## Sheet1
0
F0 | DWN (Impact to OA)
F1 | External Project Coordination
F2 | Scope Add or Change
F3 | GMP or CO Processing Delay
F4 | Supply Chain
F5 | Design Error or Omission
F6 | Funding
F7 | Resource Capacity Issue (labor)
F8 | Other (No slip reason category applies)
F9 | Schedule Updating Miss or Error
F10 | QS / Estimating Alignment
F11 | Field Quality / Rework Req
F12 | Scope/Schedule Development During Rev-0
F13 | Project Coordination
F14 | External Factors
F15 | COVID-19
F16 | Criteria/Info Miss or Delay
F17 | Design Package Delay
F18 | Incorrect Work Sequencing
F19 | Signoff / Approval Delay (DV, CC & OA)
F20 | Shutdown Schedule Change
F21 | Layout Miss or Change
F22 | Workable Backlog w/ no less than 10 days float
F23 | Unforeseen Conditions
F24 | Equipment Start Up Issue
F25 | Project Repriortization Direction
F26 | Scope/Schedule Development During Rev-1